## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-01 | Project Environment setup (SpringBoot, MySQL, IDE) | MUST HAVE | _ | Sri Kumar | 3- Completed
S1 | S1 | US-02 | Implement Task CRUD operations using thymeleaf UI | MUST HAVE | US-01 | Sri Kumar | 3- Completed
S1 | S1 | US-03 | Display Tasks in Table view | MUST HAVE | US-02 | Sri Kumar | 3- Completed
S1 | S1 | US-04 | Implemented Task creation, viewing, editing, and deletion | MUST HAVE | US-03 | Sri Kumar | 3- Completed
S2 | S2 | US-01 | Implemented CSS part for Table view | SHOULD HAVE | S1 US-04 | Sri Kumar | 3- Completed
S2 | S2 | US-02 | Implemented pagination, sorting, card view, calender view | SHOULD HAVE | S1 US-04 | Sri Kumar | 3- Completed
S2 | S2 | US-03 | Created API's for controlling | MUST HAVE | _ | Sri Kumar | 3- Completed
S3 | S3 | US-01 | Implemented user authentication using email and password | MUST HAVE | _ | Sri Kumar | 3- Completed
S3 | S3 | US-02 | Maintained user session to restrict unauthorized access | MUST HAVE | S3 US-01 | Sri Kumar | 3- Completed
S3 | S3 | US-03 | Maintain authenticated session & user-specific tasks | MUST HAVE | _ | Sri Kumar | 3- Completed
S4 | S4 | US-01 | Create A profile page for users | MUST HAVE | _ | Sri Kumar | 3- Completed
S4 | S4 | US-02 | Implementing Dashboard feature | SHOULD HAVE | _ | Sri Kumar | 3- Completed
S4 | S4 | US-03 | A csv file feature that user can download their tasks excel sheet | SHOULD HAVE | _ | Sri Kumar | 3- Completed
S4 | S4 | US-04 | Added new features like task reminder via email | MUST HAVE | S3 US-01 | Sri Kumar | 3- Completed
S4 | S4 | US-05 | MIT LICENSE | MUST HAVE | _ | Sri Kumar | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 51 | 23 | 20 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
S1-US-01 | T-1 | Setup Spring Boot project, MySQL connection, IDE configuration | 2025-12-01 | 2025-12-02 | Sri Kumar | Installation and setup | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1-US-02 | T-2 | Create Task entity, repository and service layer | 2025-12-03 | 2025-12-04 | Sri Kumar | coding | Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1-US-02 | T-3 | Design Thymeleaf UI for task creation | 2025-12-04 | 2025-12-05 | Sri Kumar | coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1-US-03 | T-4 | Display tasks in table format | 2025-12-06 | 2025-12-07 | Sri Kumar | coding | Completed | 3 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1-US-04 | T-5 | Implement view, edit, delete task functionality | 2025-12-08 | 2025-12-12 | Sri Kumar | coding | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S2-US-01 | T-6 | Add CSS styling for table view | 2025-12-15 | 2025-12-17 | Sri Kumar | coding | Completed | 2 | 30min | 30min | 30min | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S2-US-02 | T-7 | Implement pagination and sorting | 2025-12-18 | 2025-12-20 | Sri Kumar | coding | Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S2-US-02 | T-8 | Implemented card view, calendar view | 2025-12-21 | 2025-12-22 | Sri Kumar | coding | Completed | 3 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S2-US-03 | T-9 | Created API's For Controlling | 2025-12-23 | 2025-12-24 | Sri Kumar | coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S3-US-01 | T-10 | Implement user registration using email and password | 2026-01-02 | 2026-01-03 | Sri Kumar | coding | Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S3-US-01 | T-11 | Store user credentials securely in database | 2026-01-04 | 2026-01-05 | Sri Kumar | coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S3-US-02 | T-12 | Implement session management after login | 2026-01-06 | 2026-01-07 | Sri Kumar | coding | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S3-Us-03 | T-13 | Implement session management after loginImplement user-specific task visibility | 2026-01-08 | 2026-01-09 | Sri Kumar | coding | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4-US-01 | T-14 | Create a profile page | 2026-01-11 | 2026-01-12 | Sri Kumar | coding | Completed | 1 | 30min | 30min | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4-US-01 | T-15 | Completing CSS part for profile page | 2026-01-12 | 2026-01-12 | Sri Kumar | coding | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4-US-02 | T-16 | Implementing dashboard feature | 2026-01-13 | 2026-01-14 | Sri Kumar | coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4-US-02 | T-17 | CSS for dashboard page | 2026-01-14 | 2026-01-14 | Sri Kumar | coding | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4-US-03 | T-18 | giving a download button of excel sheet for tasks | 2026-01-19 | 2026-01-20 | Sri Kumar | coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4-US-04 | T-19 | Email reminders when a task is added | 2026-01-21 | 2026-01-23 | Sri Kumar | coding | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4-US-04 | T-20 | Email reminders when a tasks due date is near to end | 2026-01-24 | 2026-01-25 | Sri Kumar | coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4-US-05 | T-21 | MIT LICENSE | 2026-01-26 | 2026-01-27 | Sri Kumar | Software Licensing | Completed | 1 | 30min | 30min | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7